## Weekly Report
WEEKLY ACCOMPLISHMENT REPORT
Name: | Muhirwa Salomon |  | Report Period: | July 21 - July 28
Designation: | Data Scientist |  | Date Submitted: | 18/06/24
TASK | PROJECT | Is There Existing XMind document that could be adapted for this task (YES/No) | DATE STARTED | STATUS (IN-PROGRESS/PENDING FOR APPROVAL /COMPLETED | DATE COMPLETED | ACTUAL MINUTES SPENT | REMARKS/CHALLENGES | SUGGESTIONS / IDEAS | If not, Create X-Mind | Relevant links you want to add

## Accomplishments
Date | Accomplishments
07/22/2024 | Today, we focused on generating and saving fake user data for a database schema. We fixed an issue with a naming conflict involving the json module and successfully loaded blocked reasons from a JSON file. We adjusted the probabilities for staff and non-staff roles and ensured that non-staff users were assigned specific roles. Finally, we generated a CSV file containing the user account data with appropriate fields, including organization affiliation and blocked status. We have also Worked on building the descriptive analytics engine (by Anna Lorraine Espiloy) and we worked on the task - Create the analysis engine and the dashboard for NACB staff and organization
07/24/2024 | I have worked on creating a fake dataset for building tomorrow, Data analytic Engine. We have another task from Henry to build a document with an explanation of the roles and data objectives for them and use that to select the data points that they need to achieve their objectives as well as the dashboard strategy. Anna Lorraine Espiloy started writing query from generated dataset
07/25/2024 | Today, we analyzed a comprehensive set of datasets to determine the optimal method for integrating and visualizing the data in Tableau. I have also implemented a basic prediction Machine Learning model to predict if an organization is likely to stay or leave the platform in the future, which is useful in predictive analytics
07/26/2024 | Today, we created the analysis engine, where we built the analytic engine of the dashboard for NACB Staff, organization level, and user level, in addition to prediction models